## Sheet1
GANTT CHART
PROJECT TITLE | NHL Playoff Predictor
[5 empty] | PHASE ONE | [13 empty] | PHASE TWO | [34 empty] | PHASE THREE
TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | 09/27/2021
[5 empty] | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U
Project Proposal
Introduction & Background | Kira | 09/27/2021 | 10/04/2021 | bar: 09/27/2021 M to 09/27/2021 U
Problem Definition | Tom | 09/27/2021 | 10/04/2021 | bar: 09/27/2021 M to 09/27/2021 U
Methods | Blake | 09/27/2021 | 10/04/2021 | bar: 09/27/2021 M to 09/27/2021 U
Potential Results & Discussion | Nick & Grace | 09/27/2021 | 10/04/2021 | bar: 09/27/2021 M to 09/27/2021 U
Video Recording | All | 10/04/2021 | 10/07/2021 | bar: 09/27/2021 M to 09/27/2021 W
GitHub Page | Kira | 10/04/2021 | 10/07/2021 | bar: 09/27/2021 M to 09/27/2021 W
Model 1
Data Sourcing and Cleaning | Tom | 10/07/2021 | 10/15/2021 | bar: 09/27/2021 R to 09/27/2021 R
Model Selection | Kira | 10/15/2021 | 10/18/2021 | bar: 09/27/2021 F to 09/27/2021 U
Data Pre-Processing | Tom | 10/18/2021 | 10/25/2021 | bar: 09/27/2021 M to 09/27/2021 U
Model Coding | Kira | 10/25/2021 | 11/08/2021 | bar: 09/27/2021 M to 09/27/2021 U
Results Evaluation and Analysis | Tom | 11/08/2021 | 11/16/2021 | bar: 09/27/2021 M to 09/27/2021 M
Midterm Report | All | 11/08/2021 | 11/16/2021 | bar: 09/27/2021 M to 09/27/2021 M
Model 2
Data Sourcing and Cleaning | Grace | 10/18/2021 | 10/22/2021 | bar: 09/27/2021 M to 09/27/2021 R
Model Selection | Nick | 10/22/2021 | 10/25/2021 | bar: 09/27/2021 F to 09/27/2021 U
Data Pre-Processing | Grace | 10/25/2021 | 10/29/2021 | bar: 09/27/2021 M to 09/27/2021 R
Model Coding | Nick | 10/25/2021 | 11/19/2021 | bar: 09/27/2021 F to 09/27/2021 U; 09/27/2021 T to 09/27/2021 R
Results Evaluation and Analysis | Grace | 11/19/2021 | 11/24/2021 | bar: 09/27/2021 F to 09/27/2021 T
Model 3
Data Sourcing and Cleaning | Blake | 10/18/2021 | 10/22/2021 | bar: 09/27/2021 M to 09/27/2021 R
Model Selection | Blake | 10/22/2021 | 10/25/2021 | bar: 09/27/2021 F to 09/27/2021 U
Data Pre-Processing | Blake | 10/25/2021 | 10/29/2021 | bar: 09/27/2021 M to 09/27/2021 R
Model Coding | Blake | 10/25/2021 | 11/19/2021 | bar: 09/27/2021 F to 09/27/2021 U; 09/27/2021 T to 09/27/2021 R
Results Evaluation and Analysis | Blake | 11/19/2021 | 11/24/2021 | bar: 09/27/2021 F to 09/27/2021 T
Evaluation
Model Comparison | Tom | 11/29/2021 | 12/07/2021 | bar: 09/27/2021 M to 09/27/2021 M
Presentation | All | 11/29/2021 | 12/06/2021 | bar: 09/27/2021 M to 09/27/2021 U
Recording | All | 12/06/2021 | 12/07/2021 | bar: 09/27/2021 M
Final Report | All | 11/29/2021 | 12/07/2021 | bar: 09/27/2021 M to 09/27/2021 M